## Bid Sheet
Bid Sheet - Old Highland Library Renovation
|  | Profit | 15%
| Base Bid | Alt #1 | Alt #2 | Base Bid + Alt
Materials | 173081 | 33673 | 7619 | 214373
Labor | 45749 | 10023.75 | 4977.75 | 60750.5
Profit | 32824.5 | 6554.5125 | 1889.5125 | 41268.525
Total Bid | 251654.5 | 50251.2625 | 14486.2625 | 316392.025
My estimate on the bid maximum | 300000
Minimum profit I need | 10%
Maximum I can pay plumbers | 25

## Materials
Materials - Old Highland Library Renovation
| Base Bid | Alt #1 | Alt #2 | Base Bid + Alt
Masonary | 21451 |  |  | 21451
Wood and Plastics | 26748 | 7218 | 2154 | 36120
Doors and Windows | 12857 | 5441 | 1745 | 20043
Fire Alarm | 875 |  |  | 875
Furnishings | 22415 | 3189 |  | 25604
Electircal | 19754 | 6141 | 798 | 26693
Plumbing | 4512 | 3155 | 1164 | 8831
Finishes | 18947 | 5411 | 1758 | 26116
Mechanical | 24115 |  |  | 24115
Thermal and Moisture Protection | 3897 |  |  | 3897
Fire Protection and Suppression | 2189 |  |  | 2189
Roofing | 15321 | 3118 |  | 18439
Total Bid | 173081 | 33673 | 7619 | 214373

## Labor
Estimated Labor Costs - Old Highland Library Renovation
| Hours Estimated to Complete Work |  |  |  |  | Labor Cost
| Base Bid | Alt #1 | Alt #2 | Totals Hours | Hourly Rate Current Quotes | Base Bid | Alt #1 | Alt #2
Masonary | 215 |  |  | 215 | 29.75 | 6396.25 | 0 | 0
Carpentry | 1245 | 325 | 114 | 1684 | 18.75 | 23343.75 | 6093.75 | 2137.5
Electrical | 322 | 95 | 85.75 | 502.75 | 27 | 8694 | 2565 | 2315.25
Roofers | 96 | 21 |  | 117 | 15 | 1440 | 315 | 0
Plumbing | 235 | 42 | 21 | 298 | 25 | 5875 | 1050 | 525
Total Bid | 2113 | 483 | 220.75 | 2816.75 |  | 45749 | 10023.75 | 4977.75
|  |  | Alt #2 | Alt #1 | Base
|  |  | 4977.75 | 10023.75 | 45749 |  | 4977.75
Estimated Cost Reductions/Increases for Schedule Changes | 1-Week Early | 90% |  |  |  |  | 90%
| On Time | 100%
| 1 Week Late | 112%
| 2 Weeks Late | 126%
| 3 Weeks Late | 132%
| 4 Weeks Late | 141%

## Loan
Construction Loan - Old Highland Library Renovation
| Loan amount | 55000 |  | Term in months | 6
| Loan rate | 5.25%
| 5.25% | 5.5% | 5.75% | 6% | 6.25%
55000
60000
65000
70000
75000
80000